SIMATS ENGINEERING (SAVEETHA SCHOOL OF ENGINEERING)

Department of Computer Science and Engineering

CO1 ASSESSMENT TOOL 2  –  Agile Sprint Planning & User Story Workshop

| Course Code: | CSA10 / CSA1063 | Course Title: | Software Engineering |
| --- | --- | --- | --- |
| CO Assessed: | CO1 | Assessment: | Assessment Tool 2 – Agile Sprint Planning & User Story Workshop |
| Weightage: | 20% | Total Marks: | 25 |
| CO1 Statement: | Apply advanced methodologies and agile project management techniques to manage software projects effectively |  |  |
| Student Name: |  | Reg. No.: |  |
| Date: |  | Duration: | 60 minutes |

Code of Conduct I __________________________ (Name / Reg No) certify that this submission is my original work and that I have adhered to the guidelines specified for this assessment. I understand that any violation of academic integrity rules will result in disciplinary action. Signature of the Student: _________________________

Annexure A – Agile Sprint Planning & User Story Workshop

Instructions to Students:

Each student is assigned an individual software project problem statement. Based on the given problem statement, perform an Agile Sprint Planning and User Story Workshop by applying Agile software engineering practices. Prepare a comprehensive sprint planning document covering the following aspects:

Based on the given problem statement, perform an Agile Sprint Planning and User Story Workshop by applying Agile software engineering practices. Prepare a comprehensive sprint planning document covering the following aspects:

- Identify the Project Vision and Stakeholders

  - Define the project's vision, objectives, and identify all key stakeholders involved.

Project Title: Smart Water Purification and Quality Monitoring System for Rural and Mining-Affected Areas

Project Vision

- To give every rural and mining-affected community reliable access to safe drinking water through a low-cost, solar-powered IoT system that continuously monitors water quality, purifies it automatically and warns people before they consume unsafe water.

- Target problem: groundwater and surface water near mines are often contaminated by acid mine drainage, heavy metals (lead, arsenic, cadmium, iron), high turbidity and dissolved solids, and villages have no continuous testing facility.

Project Objectives

- Measure key water parameters (pH, turbidity, TDS, conductivity, temperature) in real time using low-cost sensors.

- Automatically trigger filtration/UV purification when readings cross safe limits (BIS 10500 / WHO guidelines).

- Send instant alerts (buzzer/LED at site, SMS to villagers and officials) when water becomes unsafe.

- Work in low-network areas using LoRa/GSM with offline data buffering.

- Provide a web dashboard and reports for health officers, mine authorities and local government to track trends.

- Run on solar power with battery backup so the system works in areas with unreliable electricity.

- Deliver the product incrementally in 2-week Agile sprints, with working software at the end of every sprint.

Key Stakeholders

| Stakeholder | Role | Interest / Expectation |
| --- | --- | --- |
| Villagers / Households | End users (primary beneficiaries) | Safe, affordable drinking water; simple alerts in local language |
| Village Panchayat / Local Body | Customer / sponsor on the ground | Manage community water points; get warnings and reports |
| District Health Department | Domain authority | Prevent waterborne diseases; access to water quality data |
| Mining Company / Mine Safety Officer | Regulated stakeholder | Monitor effluent impact; comply with environmental rules |
| State Pollution Control Board | Regulator | Compliance monitoring and audit reports |
| Field Technician | Installs and maintains units | Easy installation, calibration and filter-replacement alerts |
| Product Owner | Agile role | Owns vision and prioritised product backlog |
| Scrum Master | Agile role | Facilitates ceremonies and removes impediments |
| Development Team (4 members) | Agile role | Embedded/IoT, backend, web and QA work; delivers sprint increment |
| NGOs / Funding Agencies | Sponsors / supporters | Social impact, cost-effectiveness and scalability |
| Hardware / Sensor Suppliers | External vendors | Clear specifications and timely orders |

- Create Epics and User Stories

  - Break down the requirements into Epics and formulate well-structured User Stories using the format:
As a <user>, I want <feature>, so that <benefit>.

Epics

- E1 – Water Quality Sensing & Data Acquisition

- E2 – Automated Water Purification Control

- E3 – Connectivity & Data Management

- E4 – Alerts & Notifications

- E5 – Dashboard & Reporting

- E6 – System Administration, Security & Power Management

User Stories (format: As a <user>, I want <feature>, so that <benefit>)

E1 – Water Quality Sensing & Data Acquisition

- US-01: As a field technician, I want sensors to measure pH, turbidity, TDS and temperature every 5 minutes, so that water quality is monitored continuously without manual testing.

- US-02: As a mine safety officer, I want to be notified of sudden conductivity/TDS spikes, so that possible mine-drainage contamination is detected early.

E2 – Automated Water Purification Control

- US-03: As a villager, I want the purification unit to start filtration/UV treatment automatically when water is unsafe, so that I always get safe drinking water.

- US-04: As a field technician, I want a filter-health indicator with a replacement reminder, so that purification quality is never reduced by a clogged filter.

E3 – Connectivity & Data Management

- US-05: As a system administrator, I want sensor data sent to the cloud over LoRa/GSM with offline buffering, so that no readings are lost in weak-network areas.

- US-06: As a district health officer, I want historical readings stored, so that I can study contamination trends and plan interventions.

E4 – Alerts & Notifications

- US-07: As a villager, I want a buzzer/LED and an SMS alert in my local language when water is unsafe, so that I can avoid drinking it.

- US-08: As a panchayat head, I want critical alerts escalated to the health department, so that quick action is taken during contamination events.

E5 – Dashboard & Reporting

- US-09: As a district health officer, I want a live web dashboard showing current readings and safe/unsafe status of every station, so that I can monitor many villages from one place.

- US-10: As a pollution control board officer, I want monthly downloadable compliance reports, so that I can audit water quality near mining areas.

E6 – System Administration, Security & Power Management

- US-11: As an administrator, I want role-based login (admin, officer, technician), so that only authorised people can view or change system data.

- US-12: As a field technician, I want solar power with battery-level monitoring, so that the unit keeps working during outages and cloudy days.

- Define Acceptance Criteria

  - Write clear and measurable acceptance criteria for each selected user story using the Given–When–Then format or equivalent.

- Acceptance criteria are written in Given–When–Then format for the five stories selected for Sprint 1 (US-01, US-05, US-03, US-07, US-09).

US-01 – Real-time water quality sensing

- Given the unit is powered on, when 5 minutes elapse, then pH, turbidity, TDS and temperature are recorded and timestamped.

- Given the sensors are calibrated, when readings are compared with a reference lab kit, then pH error is within ±0.2 and TDS error within ±10%.

- Given a sensor is disconnected or gives an out-of-range value, when the reading is taken, then a "sensor fault" status is logged instead of a wrong value.

US-05 – Data transmission with offline buffering

- Given network coverage is available, when a reading is taken, then it reaches the cloud database within 30 seconds.

- Given there is no network, when readings are taken, then at least 24 hours of data is stored locally.

- Given the network returns, when the device reconnects, then all buffered data is uploaded in order with no duplicates or loss.

US-03 – Automatic purification control

- Given pH is outside 6.5–8.5 or turbidity is above 5 NTU or TDS is above 500 ppm, when the reading is processed, then the purification pump/UV unit switches ON within 10 seconds.

- Given all readings return to the safe range for 3 consecutive samples, when processed, then the unit switches to normal mode.

- Given the unit is operating, when a pump fault occurs, then the output valve closes and a fault alert is raised.

US-07 – Unsafe water alert

- Given any parameter exceeds its safe limit, when it is detected, then the on-site buzzer and red LED are activated within 5 seconds.

- Given an unsafe status is detected, when the alert is triggered, then an SMS is sent to registered numbers within 60 seconds.

- Given water returns to a safe level, when confirmed, then a "water safe" message is sent and the buzzer stops.

US-09 – Live web dashboard

- Given an officer is logged in, when the dashboard is opened, then the latest reading of each station is shown with safe/unsafe colour status.

- Given new data arrives, when the page is open, then values refresh automatically within 10 seconds without a manual reload.

- Given the dashboard is opened on a mobile browser, when it loads, then it displays correctly and loads within 3 seconds on a 4G connection.

- Prioritize the Product Backlog

  - Organize and prioritize the product backlog based on business value, customer needs, and project dependencies.

- Prioritisation method: MoSCoW (Must / Should / Could) combined with business value, community need (health risk) and technical dependency.

- Logic used: foundation first (sensing → connectivity), then core value (purification, alerts, dashboard), then enhancements (reports, escalation, security hardening).

| Rank | ID | User Story (short) | MoSCoW | Business Value | Dependency / Reason |
| --- | --- | --- | --- | --- | --- |
| 1 | US-01 | Real-time sensing of water parameters | Must | Very High | Base of the whole system; no dependency |
| 2 | US-05 | Data transmission with offline buffering | Must | Very High | Needs US-01; required for remote monitoring |
| 3 | US-03 | Automatic purification control | Must | Very High | Needs US-01; directly gives safe water |
| 4 | US-07 | Unsafe water alerts (buzzer + SMS) | Must | High | Needs US-01, US-05; protects health |
| 5 | US-09 | Live web dashboard | Must | High | Needs US-05 data in cloud |
| 6 | US-02 | Conductivity/TDS spike detection (mine drainage) | Should | High | Needs US-01, US-05 |
| 7 | US-06 | Historical data storage and trends | Should | Medium | Needs US-05 |
| 8 | US-12 | Solar power and battery monitoring | Should | Medium | Hardware task; can run parallel |
| 9 | US-08 | Alert escalation to health department | Should | Medium | Needs US-07 |
| 10 | US-11 | Role-based login | Should | Medium | Needs US-09 |
| 11 | US-04 | Filter health indicator | Could | Low | Needs US-03 |
| 12 | US-10 | Monthly compliance reports | Could | Low | Needs US-06 |

- Backlog is refined at the end of every sprint; priorities may change based on Product Owner and stakeholder feedback.

- Plan the Sprint Backlog

  - Select high-priority user stories for the first sprint and divide them into actionable development tasks.

Sprint 1 Details

- Sprint length: 2 weeks (10 working days).

- Team: Product Owner, Scrum Master and 4 developers (IoT/embedded, backend, web, QA).

- Assumed team velocity: 30 story points per sprint.

- Selected stories (top-priority "Must" items): US-01, US-05, US-03, US-07 and US-09 = 29 story points, which fits within the velocity.

Task Breakdown

US-01 – Real-time sensing (5 SP)

- T1: Select and procure pH, turbidity, TDS and temperature sensors with a microcontroller (ESP32).

- T2: Wire sensors and write sampling firmware (5-minute interval).

- T3: Calibrate sensors with standard buffer solutions.

- T4: Add sensor-fault detection and timestamping.

- T5: Unit-test readings against a reference kit.

US-05 – Data transmission & buffering (8 SP)

- T6: Set up the LoRa/GSM module and gateway.

- T7: Design the JSON data format and the cloud REST API.

- T8: Create the cloud database schema.

- T9: Implement local flash buffering and retry logic.

- T10: Test with network switched on and off.

US-03 – Automatic purification (8 SP)

- T11: Define safe-limit thresholds (BIS/WHO) in a configuration file.

- T12: Build relay circuit for pump and UV unit.

- T13: Code the threshold decision logic with hysteresis.

- T14: Add pump-fault detection and valve shut-off.

- T15: Integration test with simulated unsafe water.

US-07 – Unsafe water alerts (3 SP)

- T16: Connect buzzer and LED to the controller.

- T17: Integrate an SMS gateway API.

- T18: Create message templates (English and Tamil/local language).

- T19: Test alert delay and "water safe" message.

US-09 – Live dashboard (5 SP)

- T20: Design the dashboard wireframe.

- T21: Build the frontend with live cards and status colours.

- T22: Connect the dashboard to the backend API with auto-refresh.

- T23: Test on mobile browsers.

Common tasks (all stories)

- Daily stand-up, code review, integration testing, bug fixing, sprint review demo and retrospective.

- Estimate Effort Using Story Points

  - Assign story points to each selected user story using an appropriate estimation technique (e.g., Fibonacci sequence or Planning Poker) and justify your estimates.

- Technique: Planning Poker with the Fibonacci sequence (1, 2, 3, 5, 8, 13).

- Story points reflect effort, complexity and uncertainty together, not just time. Baseline reference story: US-07 (buzzer + SMS) = 3 points, and the other stories are compared against it.

| ID | User Story | Story Points | Justification |
| --- | --- | --- | --- |
| US-01 | Real-time sensing | 5 | Four sensors to wire and calibrate; moderate hardware risk but well-known technology. |
| US-05 | Data transmission & buffering | 8 | LoRa/GSM setup, cloud API and offline buffering with retry; highest uncertainty and integration effort. |
| US-03 | Automatic purification control | 8 | Hardware relay control, safety logic, fault handling and testing with simulated unsafe water. |
| US-07 | Unsafe water alerts | 3 | Simple output logic plus an SMS API; baseline reference story. |
| US-09 | Live dashboard | 5 | Standard web development, but needs live data, auto-refresh and mobile-friendly design. |
|  | Total | 29 | Within the assumed velocity of 30 points. |

- Estimates are agreed by the whole team after discussion; any big difference between estimates (e.g., 3 vs 8) is discussed and re-voted until consensus is reached.

- Velocity is recalculated after Sprint 1 and used to plan Sprint 2.

- Present the Sprint Goal and Expected Deliverables

  - Define a clear sprint goal and describe the expected sprint deliverables, including the features to be completed at the end of the sprint.

Sprint Goal

- "By the end of Sprint 1, deliver a working prototype that senses water quality in real time, sends the data to the cloud, automatically starts purification and raises alerts when water is unsafe, and shows the status on a live web dashboard."

Expected Deliverables

- Working sensor unit measuring pH, turbidity, TDS and temperature every 5 minutes (US-01).

- Data transmission to the cloud with offline buffering and automatic re-upload (US-05).

- Automatic purification control (pump/UV ON-OFF) based on safe-limit thresholds (US-03).

- On-site buzzer/LED and SMS alerts for unsafe water (US-07).

- Live web dashboard with safe/unsafe status of the monitoring station (US-09).

- Supporting items: circuit diagram, API documentation, test report and sprint review demo.

Definition of Done

- Code is reviewed and merged, and all acceptance criteria pass.

- Unit and integration tests are completed with no critical bugs.

- Feature is demonstrated to the Product Owner and accepted.

- Documentation is updated.

Risks and Assumptions

- Sensor accuracy drift in harsh water conditions – mitigated by calibration and fault detection.

- Weak network in remote areas – mitigated by offline buffering.

- Hardware delivery delay – mitigated by ordering components before the sprint starts.

Sprint Ceremonies

- Sprint Planning (Day 1), Daily Stand-up (15 min), Sprint Review/Demo (Day 10) and Sprint Retrospective (Day 10).

Rubrics for Calculation

| Criteria | Excellent (5 Marks) | Good (3 Marks) | Satisfactory (2 Marks) | Needs Improvement (1 Mark) |
| --- | --- | --- | --- | --- |
| Project Vision & Stakeholder Identification (30%) | Project vision is clear, comprehensive, and aligned with the problem statement. All relevant stakeholders and their roles are correctly identified. | Vision is clear with minor omissions. Most stakeholders are correctly identified. | Vision is partially defined. Some stakeholders are missing or incorrectly identified. | Vision is unclear or incomplete. Stakeholders are poorly identified or missing. |
| Epics & User Stories (25%) | Epics are well-defined and user stories are complete, follow Agile format, and fully capture functional requirements. | Epics and user stories are mostly complete with minor formatting or requirement issues. | User stories are partially complete with limited Agile structure. | User stories are incomplete, unclear, or do not follow Agile practices. |
| Acceptance Criteria (20%) | Acceptance criteria are specific, measurable, testable, and aligned with all user stories. | Acceptance criteria are mostly clear and testable with minor gaps. | Acceptance criteria are partially defined and lack clarity or completeness. | Acceptance criteria are missing or not aligned with user stories. |
| Product Backlog Prioritization & Sprint Planning (15%) | Product backlog is logically prioritized, sprint backlog is realistic, and task breakdown is complete. | Backlog prioritization and sprint planning are mostly appropriate with minor issues. | Prioritization or sprint planning is partially complete with limited justification. | Backlog prioritization and sprint planning are poorly organized or incomplete. |
| Story Point Estimation, Sprint Goal & Presentation (10%) | Story point estimation is well justified, sprint goal is clear, deliverables are realistic, and presentation is professional and well organized. | Estimation and sprint goal are mostly appropriate with minor inconsistencies. Presentation is clear. | Estimation or sprint goal lacks justification. Presentation is adequate but incomplete. | Estimation is unrealistic or missing. Sprint goal, deliverables, and presentation are unclear or incomplete. |

| Criteria | Mark |
| --- | --- |
| Project Vision & Stakeholder Identification (30%) | /5 |
| Epics & User Stories (25%) | /5 |
| Acceptance Criteria (20%) | /5 |
| Product Backlog Prioritization & Sprint Planning (15%) | /5 |
| Story Point Estimation, Sprint Goal & Presentation (10%) | /5 |
| TOTAL | /25 |